## MEPping Load Mappings
Star | Date | Time | Attempts | ODST Benchmark Fact Count | ODSD Fact Count | Dims MEP'd? | Fact MEP'd? | ODST Benchmark Time | ODSD Time | Notes
Institution | 2015-09-22 | 9:22am | 6 | 525k | 525k | y | y | 5 | 6 | Had to MEP MULTI_SOURCE cleansing rule; had to modify inst dim mapping (yes/no/no/yes, and re-sync source table); was missing 0 row in some dimensions; had cartesian in wkeys mapping, added join on wdt_institution.ua_01 = wtt_clean.mif
Academic Outcome Honor | 2015-09-22 | 11:24am | 1 | 27k | 27k | y | y | 1 | 4 | first try!
Athletic | 2015-09-22 | 11:33am | 1 | 8k | 8k | y | y | 1 | 1 | first try!
Contact | 2015-09-22 | 11:48am | 1 | 18 | 18 | Y | Y | 2 | 1 | first try!
Race | 2015-10-01 | 8:36am | 4 | 20M | 20M | Y | Y | 240 | 217 | Had to tweak dynamic sql syntax
Interest | 2015-09-22 | 1:55pm | 6 | 1M | 1M | Y | Y | 10 | 14 | Had to assign cleansing rule MULTI_SOURCE to wdt_person_details_extr; had to fix some dynamic sql for syntax errors
Post Secondary School | 2015-09-23 | 1:26pm | 8 | 6M | 6M | Y | Y | 90 | 96 | Had to tweak dynamic sql syntax; fixed post second dim inst mapping; had to add 0 row to wdt_post_secondary_school; had to fix wkeys mapping, added join on wdt_institution.ua_01 = clean.mif_wv
Prospective Student | 2015-10-01 | 11:27am | 5 | 1M | 1M | Y | Y | 18 | 18 | Had to modify wkeys mapping, needed join on inst=clean mif
Student Cohort | 2015-10-01 | 12:30pm | 5 | 165K | 249k | Y | Y | 7 | 5 | first try!
Student Activity | 2015-10-02 | 9:46AM | 1 | 12k | 12K | Y | Y | 1 | 1 | first try!
Hold | 2015-10-02 | 11:11am | 1 | 25M | 25M | Y | Y | 280 | 247 | first try!
Test | 2015-10-14 | 8:08am | 5 | 46M | 46M | Y | Y | 600 | 870 | had to modify dims (test extension, person extension, demographic extension - set cleansing for ua_01 to mif)
Student Attribute | 2015-10-02 | 2:24pm | 1 | 3M | 3M | Y | Y | 90 | 50 | first try!
Advisor | 2015-10-02 | 3:28pm | 15 | 500K | 480K | Y | Y | 15 | 19 | person dimension mapping needed heavy mods
Finaid Application | 2015-10-02 | 3:51pm | 1 | 200k | 240k | Y | Y | 4 | 6 | first try!
Grade Change | 2015-10-02 | 4:01pm | 2 | 550K | 550K | Y | Y | 15 | 11 | Had to tweak sql, removed "return" clause by mistake;
Meeting Time | 2015-10-12 | 8:37am | 1 | 70K | 62K | Y | Y | 3 | 2 | first try!
Course Instructor | 2015-10-12 | 8:43am | 1 | 45k | 51k | Y | Y | 1 | 1 | first try!
Course Section | 2015-10-12 | 8:59am | 1 | 85k | 84k | Y | Y | 2 | 1 | first try!
Student | 2015-10-12 | 9:03am | 4 | 300k | 280K | Y | Y | 30 | 23 | mst_enrollment part 2 was not loaded
Banner Communication | 2015-10-12 | 10:49am | 1 | 16M | 17M | Y | Y | 240 | 228 | first try!
Retention Multi Year | 2015-10-12 | 2:53pm | 4 | 530k | 250k | Y | Y | 15 | 5 | I think it was a data issue in that we didn't have everything fully loaded; counts off as need all student stars not yet loaded
Student Course Attribute | 2015-10-13 | 7:56am | 4 | 1.7M | 1.6M | Y | Y | 70 | 66 | data errors - they should be fixed in prod, just not in dev
Admissions Application | 2015-10-13 | 11:03am | 1 | 170K | 163K | Y | Y | 10 | 9 | first try!
FinAid Award AP | 2015-10-13 | 11:16am | 1 | 500k | 445K | Y | Y | 15 | 7 | had to fix prompt
FinAid Award AY | 2015-10-13 | 4:38pm | 1 | 250k | 231K | Y | Y | 10 | 7 | had to fix prompt
Academic Outcome | 2015-10-13 | 1:24pm | 2 | 17K | 17K | Y | Y | 1 | 1 | had bug in extract package, user error - I copied/pasted a user_attribute_01 field incorrectly
Student Course | 2013-10-14 | 7:52am | 2 | 750k | 700K | Y | Y | 40 | 25 | wkeys mapping was broken again, submitted ellucian bug & fixed mapping; mst_student_course wasn't fully loaded so counts were way low
FinAid Agg | 2015-10-27 | 11:26am | 1 | 1M | 1M | n/a | Y | 8 | 55 | first try!
Student Progress Agg | 2015-10-27 | 11:26am | 1 | 2M | 519K | n/a | Y | 25 | 13 | had to alter mapping - need to manually type in mif_value_vc to wft_student table object, a sync won't do it. Then flow it through to all other objects; need join on wft_student.mif_value_vc = wdt_person.user_attribute_01 in driving table joiner. Counts might be low (520k) as not all student years loaded
Student Engagement Agg |  |  |  | 2M |  |  |  | 5 |  | missing from admin UI as shortcut; have to run as single mapping and find it in drop down (EDW_STUD_ENGAGEMENT_AGG_INSERT)

## Chain Load
This is the correct order to run a re-load, it is how the ODSD chain runs
mapping | Year | Benchmark | Actual Time
load_dim_cleansing | all | 10 | 12
refresh_edw_dim_warehouse_entity | all | 69 | 1
load_edw_hold-P | all | 157 | 174
load_edw_institution-P | all | 6 | 6
load_edw_race-P | all | 147 | 280
load_edw_finaid_application-P | 2009 | 6 | 3
load_edw_finaid_application-P | 2010 | 6 | 3
load_edw_finaid_application-P | 2011 | 5 | 3
load_edw_finaid_application-P | 2012 | 3 | 4
load_edw_finaid_application-P | 2013 | 5 | 3
load_edw_finaid_application-P | 2014 | 6 | 8
load_edw_finaid_application-P | 2015 | 1 | 9
load_edw_finaid_awd_acadpd-P | 2009 | 7 | 14
load_edw_finaid_awd_acadpd-P | 2010 | 10 | 8
load_edw_finaid_awd_acadpd-P | 2011 | 9 | 14
load_edw_finaid_awd_acadpd-P | 2012 | 9 | 12
load_edw_finaid_awd_acadpd-P | 2013 | 10 | 11
load_edw_finaid_awd_acadpd-P | 2014 | 8 | 11
load_edw_finaid_awd_acadpd-P | 2015 | 1 | 8
load_edw_finaid_awd_aidyr-P | 2009 | 3 | 2
load_edw_finaid_awd_aidyr-P | 2010 | 6 | 2
load_edw_finaid_awd_aidyr-P | 2011 | 5 | 3
load_edw_finaid_awd_aidyr-P | 2012 | 5 | 3
load_edw_finaid_awd_aidyr-P | 2013 | 4 | 3
load_edw_finaid_awd_aidyr-P | 2014 | 4 | 3
load_edw_finaid_awd_aidyr-P | 2015 | 1 | 3
load_edw_acad_otcom_hnr-P | all | 1 | 1
load_edw_admissions_application-P | 2009 | 9 | 9
load_edw_admissions_application-P | 2010 | 12 | 11
load_edw_admissions_application-P | 2011 | 12 | 9
load_edw_admissions_application-P | 2012 | 10 | 9
load_edw_admissions_application-P | 2013 | 9 | 9
load_edw_admissions_application-P | 2014 | 9 | 9
load_edw_admissions_application-P | 2015 | 4 | 10
load_edw_advisor-P | 2009 |  | 25 | ERROR
load_edw_advisor-P | 2010 |  | 25 | ERROR
load_edw_advisor-P | 2011 |  | 25 | ERROR
load_edw_advisor-P | 2012 |  | 22 | ERROR
load_edw_advisor-P | 2013 |  | 26 | ERROR
load_edw_advisor-P | 2014 |  | 27 | ERROR
load_edw_advisor-P | 2015 |  | 29 | ERROR
load_edw_athletic-P | all | 1 | 1
load_edw_meeting_time-P | 2009 | 1 | 2
load_edw_meeting_time-P | 2010 | 1 | 1
load_edw_meeting_time-P | 2011 | 1 | 1
load_edw_meeting_time-P | 2012 | 1 | 1
load_edw_meeting_time-P | 2013 | 1 | 1
load_edw_meeting_time-P | 2014 | 1 | 1
load_edw_meeting_time-P | 2015 | 1 | 1
load_edw_grade_change-P | 2009 | 10 | 13
load_edw_grade_change-P | 2010 | 9 | 13
load_edw_grade_change-P | 2011 | 10 | 15
load_edw_grade_change-P | 2012 | 9 | 12
load_edw_grade_change-P | 2013 | 10 | 14
load_edw_grade_change-P | 2014 | 8 | 13
load_edw_grade_change-P | 2015 | 8 | 11
load_edw_interest-P | all | 6 | 15
load_edw_post_secondary-P | all | 90 | 89
load_edw_prospective_student-P | all | 19 | 19
load_edw_sec_schl_subject-P | all | 0 | 0
load_edw_student_activity-P | all | 1 | 1
load_edw_student_attribute-P | 2009 | 22 | 27
load_edw_student_attribute-P | 2010 | 16 | 30
load_edw_student_attribute-P | 2011 | 18 | 33
load_edw_student_attribute-P | 2012 | 23 | 32
load_edw_student_attribute-P | 2013 | 23 | 29
load_edw_student_attribute-P | 2014 | 25 | 34
load_edw_student_attribute-P | 2015 | 24 | 36
load_edw_student_cohort-P | 2009 | 1 | 1
load_edw_student_cohort-P | 2010 | 2 | 3
load_edw_student_cohort-P | 2011 | 1 | 1
load_edw_student_cohort-P | 2012 | 2 | 2
load_edw_student_cohort-P | 2013 | 2 | 2
load_edw_student_cohort-P | 2014 | 3 | 3
load_edw_student_cohort-P | 2015 | 2 | 4
load_edw_student_course_attrib-P | 2009 | 6 | 20
load_edw_student_course_attrib-P | 2010 | 6 | 22
load_edw_student_course_attrib-P | 2011 | 6 | 25
load_edw_student_course_attrib-P | 2012 | 3 | 21
load_edw_student_course_attrib-P | 2013 | 4 | 25 | data error, nothing we can do about that
load_edw_student_course_attrib-P | 2014 | 4 | 29 | data error, nothing we can do about that
load_edw_student_course_attrib-P | 2015 | 6 | 27 | NOTE: 2015 did not run in chain! (ran manually 11/6)
load_edw_crs_inst-P | 2009 |  | 1
load_edw_crs_inst-P | 2010 |  | 3
load_edw_crs_inst-P | 2011 |  | 1
load_edw_crs_inst-P | 2012 |  | 1
load_edw_crs_inst-P | 2013 |  | 1
load_edw_crs_inst-P | 2014 |  | 1
load_edw_crs_inst-P | 2015 |  | 1
load_edw_test-P | all | 351 | 755
load_edw_academic_outcome-P | 2009 | 1 | 1
load_edw_academic_outcome-P | 2010 | 1 | 1
load_edw_academic_outcome-P | 2011 | 1 | 1
load_edw_academic_outcome-P | 2012 | 1 | 3
load_edw_academic_outcome-P | 2013 | 1 | 1
load_edw_academic_outcome-P | 2014 | 1 | 1
load_edw_academic_outcome-P | 2015 | 1 | 1
load_edw_banner_communication-P | all | 130 | 197
load_edw_course_section-P | 2009 | 1 | 1
load_edw_course_section-P | 2010 | 1 | 1
load_edw_course_section-P | 2011 | 1 | 1
load_edw_course_section-P | 2012 | 1 | 1
load_edw_course_section-P | 2013 | 1 | 1
load_edw_course_section-P | 2014 | 1 | 1
load_edw_course_section-P | 2015 | 1 | 1
load_edw_student_course-P | 2009 | 6 | 25
load_edw_student_course-P | 2010 | 6 | 30
load_edw_student_course-P | 2011 | 6 | 35
load_edw_student_course-P | 2012 | 5 | 34
load_edw_student_course-P | 2013 | 6 | 27
load_edw_student_course-P | 2014 | 5 | 40
load_edw_student_course-P | 2015 | 3 | 30 | 2 bad rows
load_edw_contact-P | all | 1 | 10
load_edw_student_star-P | 2009 | 42 | 37
load_edw_student_star-P | 2010 | 60 | 34
load_edw_student_star-P | 2011 | 54 | 39
load_edw_student_star-P | 2012 | 58 | 31
load_edw_student_star-P | 2013 | 56 | 30
load_edw_student_star-P | 2014 | 59 | 33
load_edw_student_star-P | 2015 | 16 | 33
load_edw_retention_multi_year-P | all | 1 | 28
load_edw_adms_finaid_agg | all |  | 12
load_edw_stud_prog_agg_insert | all |  | 29
load_edw_stud_eng_aga_insert | all |  | n/a
|  | 1746 | 2993
|  | 29.1 | 49.8833